## Critical path analysis
Milestone | Duration (days) | Dependencies
1 | 26
2 | 4
3 | 9 | 2
4 | 7 | 2,3
5 | 7 | 2,3
6 | 7 | 2,3
7 | 7 | 2,3
8 | 7 | 2,3
9 | 7 | 2,3
10 | 7 | 2,3
11 | 7 | 2,3
12 | 7 | 2,3
13 | 7 | 2,3
14 | 7 | 2,3
15 | 7 | 1-14
16 | 7 | 1-14
17 | 14 | 1-16
18 | 2 | 1-17

## Gantt chart activities
| Milestones |  | Tasks | June |  | July | [6 empty] | August |  |  |  |  | September
|  |  |  | 21-24 | 25-30 | 1 | 2-8 | 9-15 | 16-22 | 23-29 | 30 | 31 | 1-5 | 6-12 | 13-19 | 20-26 | 27-31 | 1 | 2 | 3-9 | 10-16 | 17 | 18
M |  | T |  | W 10 | W 11 |  | W12 | W 13 | W 14 | W 15 | W 16 |  |  | W 17 | W 18 | W 19 | W 20 |  |  | W 21 | W 22 | W 23
1 | Project proposal report
|  | 1 | Complete project proposal report (introduction, literature review, design)
|  | 2 | Complete feature prototype of most important technical feature
|  | 3 | Submit report
2 | Infrastructure setup
|  | 4 | set up Firebase project
|  | 5 | Set up Github repository
3 | Development - Authentication
|  | 6 | Set up basic one route application
|  | 7 | Set up authentication
|  | 8 | Set up email confirmations for sign up and password changes
|  | 9 | Set up unit tests for authentication functions implemented
|  | 10 | Prepare user agreement form that users must read before signup
4 | home page
|  | 11 | prepare HTML
|  | 12 | prepare CSS
|  | 13 | create mock DB objects
|  | 14 | interactions with DB
|  | 15 | routing
|  | 16 | unit tests
|  | 17 | Prepare footer with legal information and Beta warning
|  | 18 | Restrict registration to possessors of a code - to limit legal liability until proper legal advice is sought and yet allow university assessors to test the website
5 | new trip page
|  | 19 | prepare HTML / EJS templates
|  | 20 | prepare CSS
|  | 21 | create mock DB objects
|  | 22 | interactions with DB
|  | 23 | routing
|  | 24 | unit tests
6 | contact us page
|  | 25 | prepare HTML / EJS templates
|  | 26 | prepare CSS
|  | 27 | create mock DB objects
|  | 28 | interactions with DB
|  | 29 | routing
|  | 30 | unit tests
7 | settings page
|  | 31 | prepare HTML / EJS templates
|  | 32 | prepare CSS
|  | 33 | create mock DB objects
|  | 34 | interactions with DB
|  | 35 | routing
|  | 36 | unit tests
8 | trip participants page
|  | 37 | prepare HTML / EJS templates
|  | 38 | prepare CSS
|  | 39 | create mock DB objects
|  | 40 | interactions with DB
|  | 41 | routing
|  | 42 | unit tests
9 | trip itinerary page
|  | 43 | prepare HTML / EJS templates
|  | 44 | prepare CSS
|  | 45 | create mock DB objects
|  | 46 | interactions with DB
|  | 47 | routing
|  | 48 | integrating MapQuest API to validate addresses
|  | 49 | set up logs / monitoring mechanism to see how many calls have been made and alert when approximating threshold
|  | 50 | unit tests
10 | trip polls page
|  | 51 | prepare HTML / EJS templates
|  | 52 | prepare CSS
|  | 53 | create mock DB objects
|  | 54 | interactions with DB
|  | 55 | routing
|  | 56 | unit tests
11 | trip settings page
|  | 57 | prepare HTML / EJS templates
|  | 58 | prepare CSS
|  | 59 | create mock DB objects
|  | 60 | interactions with DB
|  | 61 | routing
|  | 62 | unit tests
|  | 63 | integrating Google SendGrid API for sending emails
12 | profile personal info page
|  | 64 | prepare HTML / EJS templates
|  | 65 | prepare CSS
|  | 66 | create mock DB objects
|  | 67 | interactions with DB
|  | 68 | routing
|  | 69 | unit tests
13 | profile friends page
|  | 70 | prepare HTML / EJS templates
|  | 71 | prepare CSS
|  | 72 | create mock DB objects
|  | 73 | interactions with DB
|  | 74 | routing
|  | 75 | unit tests
14 | security
|  | 76 | configure Firestore security rules
|  | 77 | Run security scanners
15 | integrate Google Adsense
|  | 78 | Register to Google AdSense
|  | 79 | Add ads to site
16 | payment integration
|  | 80 | Integrate Stripe and register payment history
|  | 81 | Implement Pro features mechanism
17 | Final report
|  | 82 | Write final report
|  | 83 | Prepare final video presentation
|  | 84 | Keep progress logs
18 | Submit final project and report